## For 3.16.12 Meeting
Client | Project Phase | Project Status | Director | Manager | Current Staffing (FTE's) | Staffing Status | Potential Follow On | Staffing Needs | Notes
All American Container (TriBridge) | remove | Green | Marker | Brown | 1 | Green |  | 0
AmeriFresh | Imp | Green | Drohan | Samuelson | 4 | Green |  | 0 | Amerifresh is in BRD and development phase, going well, Phase 2 SOW has been settled.
Arthur Middleton | Phase 4 | Yellow | Yaceczko | McKelley | 1.5 | Green |  | 0 | Last Payment from past due is this month and they are current with all prepaid work plus looking to utilize more resources for New division implementation.
Associa Upgrade | Post Imp Support | Green | Tickner | Whitcomb | 4.5 | Green
Century Martial Arts | Imp | Green | Homan | Donovan | 4 | Green |  | 0 | Workinng on SOW for phase 2. Estimated end date sometime in 2013
Daisy | Imp | Green | Johnson | Booth | 4 | Green |  | 0 | Go live support is ending, year end close is going fine. Working now on costing BRDS for "Delayed" Actuals costing model. Plan on going live March 1.
Driscoll | Imp | Green | Sloan | Dyslin | 4 | Green |  | 0 | Going well. Looking at 2011 planning and projects
Fanatics | Imp | Yellow | Derevensky | Derevensky | 14 | Green |  | 0 | The new proposed Go-Live date for Fanatics South is being scheduled for 05/14. Fanatics North Go-live sometime after that..
Gay Lea | Development | Green | Jones | Marks | 5.5 | Green |  |  | Go-Live is scheduled for early April.
Growers Express | Imp | Yellow | Drohan | Drohan | 1 | Green |  | 0 | Client has changed their requirements near the end of the project. Discussions occurring regarding options to achieve resolution.
HEB (Genetic Optimizer Development) | Imp | Green | Bova | Whiteman | 3 | Green |  | 0 | Implementing HEB San Antonio Dairy (2009). Looking good. Updating / merging code with JS 5.3. Producing a very good schedule, however, are finding new requirements. Currently waiting on HEB to do there side of things.
L&M | Post Imp Support | Yellow | Johnson | Johnson | 2 | Green |  | 0 | Wen and Phil remote support full time likely through Feb/March 2012
Lyons Magnus |  | Green | Sloan | Dart | 4 | Green
Marquez Brothers |  | Green | Sloan | Myslenski | 4 | Green |  |  | Executive kickoff in March
Oxford Mining | Post Imp Support | Green | Yaceczko | McKelley | 0 | Green |  |  | Quote for Bi360 submitted with SOW for 1 FTE, waiting for sign off
Rejuvenation - Web Integration | Imp | Green | Homan | Samuelson | 0.5 | Green |  | 0 | Rejuvenation has postponed their go-live to allow for more time to do end to end testing with the new web site.
Royal Canadian Mint | Startup | Green | Jones | Winkeler | 11 | Green |  | 0 | We actually have 9 concurrent work streams going on at this time. We have absorbed 5 green beans on the project as of now and may need additional development resources in the future.
Sakata Seed | Imp | Green | Drohan | Bell | 4 | Green |  | 0 | Reviewing the large number of customizations that were made to SAI’s 3.0 install. Modifications required to replace a highly customized Quality module. Reviewing and defining combined business processes as ACS is brought onto DAX from MAS 90.
Shamrock Dairy Implementation | Startup | Green | Johnson | Sohl | 3 | Green |  |  | Project Kickoff scheduled for 3/26.
SIFCO | Phase 3 | Green | Yaceczko | Yaceczko | 0 | Green |  |  | Budgeting & SOW for new implementation of acquired company and scheduling for 2012 upgrade for other 2 divisions in 2012. Staffing needs will be 5/7 FTE's but will not kick off till May
Simone Pearce | Support | Green | Carpen | Tickner | 0 | Green |  | 0
Smith Dairy | Phase 2 | Green | Johnson | Sohl | 3.25 | Green |  | 0 | Go Scheduler is currently being tested for User Acceptance in their Live environment and is looking to go live in March. We are also doing on-site, on-going support of various projects.
Superstores | Imp | Green | Sloan | White | 3 | Green |  | Senior functional TNL for about 2 weeks | 2/26 and 7/7 scheduled Go-lives. Should be shedding some staff in the next 4-6 weeks.
Taylor Farms | Imp | Green | Hutter | Greenwood | 8 | Green |  | 0 | Colorado project Go-Live Feb 1. PTI project behind schedule due to client. Estimated Project end Date 12/31/2012.
TricorBraun | Imp | Green | Neal | Shedelbower | 8 | Green |  | 0 | Preparations are in place to begin China, Mexico (April 1st), and develop a web storefront.
Zorch | Imp | Yellow | Neal | McLaughlin | 0.5 | Green |  | 0 | Phase-1 hard go-live on 1/2/2012. Good probability that staffing will fall to 4 to 5 FTE’s getting into Q1 of 2012. Phase-2 expected to go through Q1 into early Q2 (additional vendors, customers items, users). Phase-3 tentatively includes upgrade to AX 2012 in the Q2 timeframe.
Backlog
Horizons | Upgrade | Green | Yaceczko | Yaceczko | 0 | Green |  |  | Flipped account Mid February and are now beginning SOW Prep for Upgrade to 2012
Project Status Key
|  | Green | On target
|  | Yellow | Behind schedule/client complaining/still collecting fees on-time
|  | Red | Troubled Project/not charging or aging A/R
Staffing Status Key
|  | Green | Properly staffed
|  | Yellow | Wrong mix of staff
|  | Red | Significant staffing gaps/short of people